## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Team Meeting 2
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Member 7 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Harish | Amrita | Anusha | Mehul | Elliot | Nicklaus | Daniel | Alex
Team member's mood during the this week's meeting: |  |  | Happy | Excited | Happy | Happy | Happy | Happy | Happy | Excited
1 | System Requirement Specification - Problem Statement | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 10 | 8 | 9 | 10 | 9 | 8.875 | 5.625 | 4.25 | Amrita | Anusha | Through Discussion | Yes | 2 | Happy | 9.375
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 10 | 8 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 4 | 5 | 7 | 6 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 3 | 5 | 5 | 2 | 4 | 5 | 6
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 10 | 10 | 10 | 9 | 10
2 | System Requirement Specification - Overview | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 8 | 8 | 10 | 9.875 | 5.75 | 4.125 | Anusha | Amrita | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 6 | 4 | 6 | 7 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 5 | 3 | 4 | 5 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 9 | 9 | 10 | 7 | 7 | 9
3 | System Requirement Specification - Investigation & Analysis Methodology | Task Quality Evaluation (After Task Completed) | 8 | 10 | 7 | 9 | 9 | 10 | 8 | 8 | 6.625 | 6.25 | 3.875 | Alex | Nicklaus | Through Discussion | Yes | 1 | Happy | 8.625
| Estimated Task Priority（0-10） |  | 7 | 6 | 8 | 5 | 6 | 7 | 8 | 6
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 8 | 5 | 7 | 7 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 3 | 3 | 2 | 4 | 4 | 4 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 9 | 10 | 9 | 8 | 8 | 10
4 | System Requirement Specification - Constraints | Task Quality Evaluation (After Task Completed) | 9 | 10 | 8 | 9 | 7 | 10 | 7 | 9 | 7.375 | 6.875 | 4.625 | Amrita | Anusha | Through Discussion | Yes | 2 | Happy | 8.625
| Estimated Task Priority（0-10） |  | 7 | 8 | 8 | 8 | 6 | 8 | 7 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 8 | 6 | 7 | 5 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 5 | 5 | 4 | 6 | 5 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 8 | 7 | 8 | 6 | 8 | 9
5 | System Requirement Specification - Operational Requirements | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 9 | 10 | 8 | 7 | 10 | 5.375 | 6 | 3.875 | Daniel | Elliot | Through Discussion | Yes | 1 | Happy | 8.75
| Estimated Task Priority（0-10） |  | 5 | 6 | 4 | 5 | 5 | 7 | 6 | 5
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 6 | 5 | 5 | 6 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 5 | 3 | 3 | 4 | 6 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 9 | 10 | 9 | 10 | 9 | 7
6 | System Requirement Specification - Functional Requirements | Task Quality Evaluation (After Task Completed) | 10 | 8 | 9 | 8 | 10 | 9 | 9 | 9 | 7.375 | 5.25 | 3.25 | Elliot | Daniel | Through Discussion | Yes | 1 | Happy | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 8 | 6 | 9 | 8 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 5 | 4 | 4 | 6 | 5 | 5 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 4 | 3 | 2 | 4 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 10 | 9 | 8 | 9 | 8
7 | System Requirement Specification - Non-Functional Requirements | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5.375 | 3.625 | 2.625 | Harish | Mehul | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 5 | 6 | 7 | 4 | 5 | 6 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 3 | 5 | 2 | 3 | 5 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 2 | 3 | 2 | 2 | 4 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 10 | 8 | 8 | 9 | 10 | 9
8 | System Requirement Specification - Process Requirements | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 10 | 8 | 8 | 8 | 8 | 8.375 | 6.5 | 6.25 | Mehul | Nicklaus | Through Discussion | Yes | 3 | Happy | 8.375
| Estimated Task Priority（0-10） |  | 8 | 9 | 7 | 7 | 8 | 9 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 6 | 8 | 6 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 7 | 6 | 8 | 5 | 5 | 6 | 7 | 6
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 10 | 8 | 9 | 10 | 8 | 9
9 | System Requirement Specification - Input Requirements | Task Quality Evaluation (After Task Completed) | 9 | 7 | 9 | 8 | 9 | 7 | 9 | 10 | 6.875 | 6 | 5.875 | Mehul | Alex | Through Discussion | Yes | 3 | Happy | 8.5
| Estimated Task Priority（0-10） |  | 6 | 7 | 7 | 6 | 7 | 6 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 4 | 6 | 6 | 7 | 6 | 6 | 8 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 6 | 7 | 4 | 8 | 5 | 6 | 5
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 9 | 10 | 9 | 8 | 10
10 | System Requirement Specification - Output Requirements | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 8 | 9 | 10 | 10 | 7 | 6.5 | 5.5 | Alex | Daniel | Through Discussion | Yes | 4 | Happy | 9.25
| Estimated Task Priority（0-10） |  | 8 | 5 | 6 | 6 | 7 | 8 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 7 | 6 | 9 | 4 | 8 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 6 | 7 | 4 | 5 | 7 | 5 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 9 | 10 | 8 | 8 | 10 | 8
11 | System Requirement Specification - Hardware Requirements | Task Quality Evaluation (After Task Completed) | 9 | 10 | 7 | 7 | 8 | 9 | 8 | 9 | 8.125 | 6.625 | 3.125 | Nicklaus | Harish | Through Discussion | Yes | 2 | Happy | 8.375
| Estimated Task Priority（0-10） |  | 8 | 9 | 10 | 6 | 7 | 9 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 8 | 6 | 9 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 4 | 2 | 2 | 3 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 10 | 10 | 9 | 9 | 9 | 8
12 | System Requirement Specification - Software Requirements | Task Quality Evaluation (After Task Completed) | 8 | 10 | 9 | 10 | 8 | 7 | 7 | 9 | 7.625 | 4.5 | 1.875 | Harish | Elliot | Through Discussion | Yes | 1 | Happy | 8.5
| Estimated Task Priority（0-10） |  | 9 | 6 | 9 | 9 | 7 | 6 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 3 | 5 | 7 | 4 | 5 | 5 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 1 | 1 | 3 | 4 | 2 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 10 | 9
13 | System Requirement Specification - Deployment Requirements | Task Quality Evaluation (After Task Completed) | 10 | 9 | 10 | 8 | 9 | 10 | 10 | 8 | 8.375 | 7.875 | 5.75 | Anusha | Mehul | Through Discussion | Yes | 4 | Happy | 9.25
| Estimated Task Priority（0-10） |  | 8 | 10 | 9 | 10 | 9 | 7 | 6 | 8
| Estimated Task Difficulty（0-10） |  | 8 | 9 | 7 | 7 | 8 | 7 | 9 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 6 | 5 | 7 | 6 | 4 | 6 | 7 | 5
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 7 | 9 | 10 | 9 | 9 | 7
14 | System Requirement Specification - Appendix A | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 9 | 10 | 9 | 7 | 9 | 5.125 | 2.625 | 2 | Alex | Elliot | Through Discussion | Yes | 1 | Happy | 9.125
| Estimated Task Priority（0-10） |  | 5 | 6 | 4 | 5 | 6 | 7 | 3 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 4 | 4 | 2 | 3 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 3 | 2 | 3 | 1 | 2 | 3 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 9 | 10 | 10
15 | Quality Management Plan - Purpose and Scope | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 6 | 4.125 | 2.625 | Harish | - | Through Discussion | Yes | 1 | Happy | 9.75
| Estimated Task Priority（0-10） |  | 7 | 5 | 6 | 6 | 7 | 5 | 5 | 7
| Estimated Task Difficulty（0-10） |  | 5 | 4 | 3 | 4 | 5 | 4 | 3 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 2 | 2 | 4 | 1 | 3 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 | 9 | 9 | 10 | 9 | 8
16 | Quality Management Plan - Reference Documents | Task Quality Evaluation (After Task Completed) | 10 | 9 | 10 | 10 | 10 | 9 | 8 | 10 | 4.375 | 3.625 | 1.625 | Amrita | - | Through Discussion | Yes | 1 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 5 | 4 | 3 | 5 | 6 | 4 | 3 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 5 | 3 | 5 | 4 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 2 | 1 | 1 | 3 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 10 | 9 | 8 | 10 | 10 | 9
17 | Quality Management Plan - Management | Task Quality Evaluation (After Task Completed) | 9 | 7 | 8 | 10 | 9 | 8 | 7 | 8 | 7.875 | 7.875 | 5.25 | Harish | - | Through Discussion | Yes | 3 | Happy | 8.25
| Estimated Task Priority（0-10） |  | 6 | 7 | 9 | 8 | 9 | 6 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 9 | 7 | 8 | 9 | 7 | 8 | 6 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 8 | 4 | 5 | 5 | 6 | 4 | 5
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 9
18 | Quality Management Plan - Documents | Task Quality Evaluation (After Task Completed) | 7 | 9 | 10 | 9 | 8 | 10 | 10 | 9 | 6.5 | 6.875 | 3.625 | Daniel | Nicklaus | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 8 | 6 | 5 | 7 | 5 | 7 | 8 | 6
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 4 | 8 | 9 | 7 | 6 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 5 | 3 | 2 | 3 | 5 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 9 | 7 | 9 | 10 | 8
19 | Quality Management Plan - Standards, Practice, Conventions and Metrics | Task Quality Evaluation (After Task Completed) | 10 | 9 | 8 | 9 | 8 | 8 | 9 | 10 | 3.125 | 3.25 | 2 | Nicklaus | Anusha | Through Discussion | Yes | 1 | Happy | 8.875
| Estimated Task Priority（0-10） |  | 4 | 3 | 2 | 4 | 5 | 2 | 2 | 3
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 5 | 3 | 2 | 3 | 4 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 4 | 1 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 9
20 | Quality Management Plan - Software Reviews | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 10 | 10 | 9 | 8 | 9 | 4.625 | 3.75 | 3.625 | Daniel | - | Through Discussion | Yes | 1 | Happy | 9
| Estimated Task Priority（0-10） |  | 4 | 5 | 6 | 4 | 6 | 3 | 4 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 5 | 5 | 4 | 3 | 3 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 5 | 4 | 4 | 3 | 5 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 9 | 10 | 9 | 8 | 10 | 8
21 | Quality Management Plan - Test | Task Quality Evaluation (After Task Completed) | 10 | 7 | 10 | 9 | 10 | 8 | 9 | 7 | 5.375 | 3.625 | 1.625 | Daniel | Amrita | Through Discussion | Yes | 4 | Happy | 8.75
| Estimated Task Priority（0-10） |  | 6 | 7 | 4 | 8 | 3 | 5 | 6 | 4
| Estimated Task Difficulty（0-10） |  | 5 | 2 | 4 | 3 | 3 | 5 | 3 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 1 | 1 | 3 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 7 | 10 | 9 | 8 | 9 | 8 | 10
22 | Quality Management Plan - Problem Reporting and Corrective Action | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 9 | 10 | 9 | 10 | 10 | 7.625 | 7.375 | 4.25 | Alex | - | Through Discussion | Yes | 2 | Happy | 9.625
| Estimated Task Priority（0-10） |  | 7 | 7 | 9 | 8 | 9 | 5 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 8 | 9 | 7 | 8 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 3 | 3 | 6 | 5 | 4 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 9 | 10 | 9 | 10 | 10 | 8
23 | Quality Management Plan - Tools, Techniques and Methodologies | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5.375 | 2.625 | 1.375 | Elliot | - | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 5 | 3 | 5 | 6 | 8 | 6 | 4 | 6
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 4 | 3 | 2 | 1 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 7 | 10 | 10 | 9 | 10 | 9 | 9
24 | Quality Management Plan - Media Control | Task Quality Evaluation (After Task Completed) | 8 | 8 | 10 | 10 | 9 | 9 | 8 | 9 | 5.875 | 3.25 | 3 | Nicklaus | Mehul | Through Discussion | Yes | 1 | Happy | 8.875
| Estimated Task Priority（0-10） |  | 7 | 6 | 4 | 6 | 5 | 8 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 3 | 5 | 2 | 3 | 4 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 5 | 4 | 2 | 3 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 9 | 8 | 10 | 10 | 9 | 9
25 | Quality Management Plan - Record Collection, Maintenance, and Retention | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 9 | 10 | 8 | 10 | 9 | 6.125 | 4.375 | 2.5 | Elliot | - | Through Discussion | Yes | 1 | Happy | 9
| Estimated Task Priority（0-10） |  | 6 | 7 | 6 | 7 | 6 | 6 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 5 | 6 | 4 | 5 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 4 | 2 | 3 | 4 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 9
26 | Quality Management Plan - Training | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 5.75 | 2.625 | 2 | Alex | Amrita | Through Discussion | Yes | 1 | Happy | 9
| Estimated Task Priority（0-10） |  | 7 | 8 | 4 | 5 | 6 | 7 | 6 | 3
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 3 | 2 | 3 | 2 | 4 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 9 | 7 | 9 | 10 | 8 | 10
27 | Quality Management Plan - Risk Management | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 10 | 9 | 8 | 10 | 7 | 9.25 | 5.375 | 3.75 | Mehul | Elliot | Through Discussion | Yes | 2 | Happy | 9.125
| Estimated Task Priority（0-10） |  | 9 | 8 | 9 | 10 | 10 | 9 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 5 | 6 | 3 | 4 | 7 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 4 | 4 | 5 | 5 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 9
28 | Quality Management Plan - SQA Plan Change Procedure and History | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 10 | 10 | 10 | 10 | 8 | 5.5 | 2.625 | Harish | Alex | Through Discussion | Yes | 1 | Happy | 9.75
| Estimated Task Priority（0-10） |  | 9 | 8 | 7 | 6 | 7 | 8 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 4 | 7 | 5 | 8 | 4 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 1 | 2 | 2 | 4 | 2 | 5
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 6 | 9 | 10 | 8 | 10 | 8
29 | Code Prototype System with Basic Functionality | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9.5 | 9.625 | 10.375 | Mehul | Anusha | Through Discussion | Yes | 7 | Happy | 10
| Estimated Task Priority（0-10） |  | 9 | 10 | 8 | 10 | 10 | 10 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 10 | 9 | 10 | 10 | 10 | 9 | 10 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 10 | 11 | 9 | 12 | 10 | 9 | 13 | 9
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 10 | 9 | 10 | 10 | 10