## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## Team Meeting 5
Task No. | Task Description | Team Member Name: | Team Leader | Member 1 | Member 2 | Member 3 | Member 4 | Member 5 | Member 6 | Member 7 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Kalki | Amrita | Anusha | Mehul | Elliot | Nicklaus | Daniel | Alex
Team member's mood during the this week's meeting: |  |  | Excited | Excited | Excited | Excited | Excited | Excited | Excited | Excited
1 | CMMI level 2 definition - Executive Summary | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 10 | 8 | 9 | 10 | 9 | 8.875 | 5.625 | 3.5 | Daniel | Kalki | Through Discussion | Yes | 2 | Happy | 9.375
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 10 | 8 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 4 | 5 | 7 | 6 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 3 | 3 | 5 | 2 | 4 | 4 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 10 | 10 | 10 | 9 | 10
2 | CMMI level 2 definition - Description | Task Quality Evaluation (After Task Completed) | 9 | 10 | 7 | 7 | 8 | 9 | 8 | 9 | 8.125 | 6.625 | 3 | Alex | Elliot | Through Discussion | Yes | 2 | Happy | 8.375
| Estimated Task Priority（0-10） |  | 8 | 9 | 10 | 6 | 7 | 9 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 8 | 6 | 9 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 3 | 2 | 3 | 3 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 10 | 10 | 9 | 9 | 9 | 8
3 | CMMI level 2 definition - Requirement Management | Task Quality Evaluation (After Task Completed) | 8 | 9 | 8 | 10 | 8 | 8 | 8 | 8 | 8.375 | 6.5 | 4.875 | Nicklaus | Kalki | Through Discussion | Yes | 3 | Happy | 8.375
| Estimated Task Priority（0-10） |  | 8 | 9 | 7 | 7 | 8 | 9 | 10 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 6 | 8 | 6 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 5 | 5 | 6 | 5 | 6 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 7 | 10 | 8 | 9 | 10 | 8 | 9
4 | CMMI level 2 definition - Project Planning | Task Quality Evaluation (After Task Completed) | 10 | 8 | 8 | 9 | 10 | 9 | 10 | 8 | 7.875 | 6.5 | 3.625 | Elliot | Nicklaus | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 7 | 9 | 8 | 8 | 8 | 8 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 9 | 5 | 6 | 4 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 3 | 4 | 4 | 3 | 4 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 9 | 7 | 9 | 7 | 9 | 8
5 | CMMI level 2 definition - Software Quality Assurance | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 8 | 9 | 10 | 8 | 10 | 8.375 | 7.875 | 3.75 | Kalki | Alex | Through Discussion | Yes | 2 | Happy | 9.125
| Estimated Task Priority（0-10） |  | 10 | 7 | 8 | 8 | 10 | 7 | 8 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 10 | 7 | 8 | 6 | 9 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 5 | 4 | 4 | 4 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 7 | 10 | 8 | 6 | 6 | 9 | 8 | 6
6 | CMMI level 2 definition - Configuration Management | Task Quality Evaluation (After Task Completed) | 8 | 10 | 10 | 9 | 8 | 9 | 10 | 10 | 6 | 3.125 | 3.375 | Daniel | Alex | Through Discussion | Yes | 3 | Happy | 9.25
| Estimated Task Priority（0-10） |  | 7 | 6 | 8 | 5 | 6 | 7 | 3 | 6
| Estimated Task Difficulty（0-10） |  | 3 | 1 | 4 | 4 | 2 | 4 | 2 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 5 | 5 | 4 | 2 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 10 | 9 | 10 | 8 | 10 | 9
7 | CMMI level 2 definition - Approvals | Task Quality Evaluation (After Task Completed) | 9 | 10 | 7 | 8 | 9 | 10 | 7 | 8 | 7.625 | 4.5 | 1.625 | Kalki | Daniel | Through Discussion | Yes | 1 | Happy | 8.5
| Estimated Task Priority（0-10） |  | 9 | 6 | 9 | 9 | 7 | 6 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 3 | 5 | 7 | 4 | 5 | 5 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 2 | 3 | 1 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 10 | 9
8 | CMMI level 2 definition - CMMI audit checklist | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 9 | 8 | 9 | 5.125 | 2.625 | 1.75 | Nicklaus | Kalki | Through Discussion | Yes | 1 | Happy | 9.25
| Estimated Task Priority（0-10） |  | 5 | 6 | 4 | 5 | 6 | 7 | 3 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 4 | 4 | 2 | 3 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 2 | 3 | 1 | 2 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 8 | 10 | 10 | 10 | 8 | 9 | 10 | 10
9 | CMMI level 2 definition - CMMI interview affirmation questions | Task Quality Evaluation (After Task Completed) | 10 | 9 | 10 | 8 | 10 | 9 | 10 | 9 | 6.875 | 6.75 | 3.5 | Elliot | Alex | Through Discussion | Yes | 2 | Happy | 9.375
| Estimated Task Priority（0-10） |  | 7 | 8 | 6 | 7 | 6 | 8 | 6 | 7
| Estimated Task Difficulty（0-10） |  | 6 | 8 | 9 | 6 | 7 | 4 | 7 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 3 | 4 | 3 | 5 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 10 | 9 | 8 | 10 | 6 | 9 | 8
10 | Test Plan - Test Plan Identifier | Task Quality Evaluation (After Task Completed) | 8 | 9 | 10 | 9 | 10 | 9 | 8 | 10 | 4.375 | 3.625 | 1.875 | Nicklaus | Alex | Through Discussion | Yes | 1 | Happy | 9.125
| Estimated Task Priority（0-10） |  | 5 | 4 | 3 | 5 | 6 | 4 | 3 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 5 | 3 | 5 | 4 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 10 | 9 | 9 | 10 | 10 | 9
11 | Test Plan - Introduction | Task Quality Evaluation (After Task Completed) | 7 | 9 | 10 | 9 | 8 | 10 | 10 | 9 | 6.5 | 6.875 | 3.625 | Nicklaus | Elliot | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 8 | 6 | 5 | 7 | 5 | 7 | 8 | 6
| Estimated Task Difficulty（0-10） |  | 7 | 6 | 4 | 8 | 9 | 7 | 6 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 5 | 3 | 2 | 3 | 5 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 9 | 9 | 8 | 9 | 7 | 9 | 10 | 8
12 | Test Plan - Test Items | Task Quality Evaluation (After Task Completed) | 9 | 7 | 8 | 10 | 9 | 8 | 7 | 8 | 7.875 | 7.875 | 4.625 | Nicklaus | Kalki | Through Discussion | Yes | 3 | Happy | 8.25
| Estimated Task Priority（0-10） |  | 6 | 7 | 9 | 8 | 9 | 6 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 9 | 7 | 8 | 9 | 7 | 8 | 6 | 9
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 5 | 4 | 5 | 4 | 5 | 4 | 5
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 9
13 | Test Plan - Features To Be Tested | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 9 | 10 | 9 | 10 | 10 | 7.625 | 7.25 | 3.875 | Elliot | Daniel | Through Discussion | Yes | 2 | Happy | 9.625
| Estimated Task Priority（0-10） |  | 7 | 7 | 9 | 8 | 9 | 5 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 7 | 9 | 8 | 8 | 7 | 8 | 5 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 5 | 3 | 3 | 4 | 5 | 4 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 9 | 10 | 9 | 10 | 10 | 8
14 | Test Plan - Features Not To Be Tested | Task Quality Evaluation (After Task Completed) | 10 | 9 | 9 | 9 | 9 | 8 | 8 | 10 | 9.875 | 5.75 | 3.625 | Elliot | Kalki | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 9 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 5 | 6 | 6 | 4 | 6 | 7 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 4 | 3 | 4 | 3 | 4 | 4
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 9 | 9 | 10 | 7 | 7 | 9
15 | Test Plan - Test Plan Identifier | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 10 | 8 | 9 | 10 | 9 | 8.875 | 5.125 | 3.75 | Elliot | Nicklaus | Through Discussion | Yes | 3 | Happy | 9.375
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 10 | 8 | 8 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 6 | 6 | 4 | 5 | 5 | 4 | 6 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 3 | 5 | 4 | 2 | 4 | 5 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 9 | 10 | 10 | 10 | 9 | 10
16 | Test Plan - Item Pass/Fail Criteria | Task Quality Evaluation (After Task Completed) | 10 | 8 | 8 | 9 | 10 | 9 | 10 | 8 | 7.875 | 6.5 | 3.875 | Kalki | Elliot | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 7 | 9 | 8 | 8 | 8 | 8 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 8 | 7 | 9 | 5 | 6 | 4 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 3 | 5 | 4 | 3 | 5 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 8 | 9 | 7 | 9 | 7 | 9 | 8
17 | Test Plan - Suspension Criteria And Resumption Requirements | Task Quality Evaluation (After Task Completed) | 9 | 8 | 8 | 10 | 9 | 8 | 10 | 8 | 7.375 | 5.75 | 3.625 | Kalki | Daniel | Through Discussion | Yes | 2 | Happy | 8.75
| Estimated Task Priority（0-10） |  | 7 | 8 | 7 | 8 | 6 | 8 | 8 | 7
| Estimated Task Difficulty（0-10） |  | 6 | 7 | 7 | 5 | 5 | 4 | 5 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 4 | 4 | 5 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 8 | 7 | 8 | 6 | 8 | 9
18 | Test Plan - Test Deliverables | Task Quality Evaluation (After Task Completed) | 10 | 8 | 9 | 8 | 10 | 9 | 9 | 9 | 7.375 | 5.25 | 3.25 | Kalki | Nicklaus | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 8 | 6 | 9 | 8 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 5 | 4 | 4 | 6 | 5 | 5 | 7 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 4 | 2 | 4 | 3 | 2 | 4 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 10 | 9 | 8 | 9 | 8
19 | Test Plan - Testing Tasks | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 8 | 9 | 10 | 8 | 10 | 7.5 | 7.875 | 3.5 | Daniel | Alex | Through Discussion | Yes | 2 | Happy | 9.125
| Estimated Task Priority（0-10） |  | 10 | 7 | 8 | 8 | 3 | 7 | 8 | 9
| Estimated Task Difficulty（0-10） |  | 7 | 8 | 10 | 7 | 8 | 6 | 9 | 8
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 4
| Team Member's Confidence about the Task (0-10) |  | 7 | 10 | 8 | 6 | 6 | 9 | 8 | 6
20 | Tset Plan - Environmental Needs | Task Quality Evaluation (After Task Completed) | 8 | 8 | 10 | 10 | 9 | 9 | 9 | 9 | 5.875 | 3.25 | 3 | Daniel | Elliot | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 7 | 6 | 4 | 6 | 5 | 8 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 3 | 5 | 2 | 3 | 4 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 4 | 5 | 4 | 2 | 3 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 7 | 8 | 9 | 8 | 10 | 10 | 9 | 9
21 | Test Plan - Responsibilities | Task Quality Evaluation (After Task Completed) | 9 | 9 | 8 | 9 | 10 | 8 | 10 | 9 | 6.125 | 4.375 | 1.75 | Daniel | Nicklaus | Through Discussion | Yes | 1 | Happy | 9
| Estimated Task Priority（0-10） |  | 6 | 7 | 6 | 7 | 6 | 6 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 5 | 6 | 4 | 5 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 9
22 | Tset Plan - Staffing And Training Needs | Task Quality Evaluation (After Task Completed) | 9 | 8 | 9 | 9 | 9 | 9 | 9 | 10 | 5.75 | 2.625 | 2.125 | Alex | Daniel | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 7 | 8 | 4 | 5 | 6 | 7 | 6 | 3
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 3 | 2 | 3 | 2 | 4 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 9 | 7 | 9 | 10 | 8 | 10
23 | Test Plan - Schedule | Task Quality Evaluation (After Task Completed) | 8 | 10 | 9 | 10 | 8 | 7 | 7 | 9 | 7.625 | 4.5 | 1.875 | Alex | Kalki | Through Discussion | Yes | 2 | Happy | 8.5
| Estimated Task Priority（0-10） |  | 9 | 6 | 9 | 9 | 7 | 6 | 7 | 8
| Estimated Task Difficulty（0-10） |  | 3 | 5 | 7 | 4 | 5 | 5 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 1 | 1 | 3 | 4 | 2 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 10 | 9
24 | Test Plan - Risks And Contingencies | Task Quality Evaluation (After Task Completed) | 9 | 10 | 7 | 7 | 8 | 9 | 8 | 9 | 8.125 | 6.625 | 3.125 | Alex | Elliot | Through Discussion | Yes | 2 | Happy | 8.375
| Estimated Task Priority（0-10） |  | 8 | 9 | 10 | 6 | 7 | 9 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 6 | 5 | 7 | 8 | 6 | 9 | 6 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 4 | 2 | 2 | 3 | 5 | 4
| Team Member's Confidence about the Task (0-10) |  | 8 | 9 | 10 | 10 | 9 | 9 | 9 | 8
25 | Test Plan - Approvals | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 9 | 8 | 9 | 5.125 | 2.625 | 2 | Nicklaus | Kalki | Through Discussion | Yes | 1 | Happy | 9.25
| Estimated Task Priority（0-10） |  | 5 | 6 | 4 | 5 | 6 | 7 | 3 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 4 | 4 | 2 | 3 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 3 | 2 | 3 | 1 | 2 | 3 | 1
| Team Member's Confidence about the Task (0-10) |  | 8 | 10 | 10 | 10 | 8 | 9 | 10 | 10
26 | Test Cases and Requirements Test Coverage Report - User Authentication | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 9 | 10 | 9 | 10 | 10 | 7.375 | 4.375 | 3.25 | Amrita | Mehul | Through Discussion | Yes | 2 | Happy | 9.625
| Estimated Task Priority（0-10） |  | 6 | 8 | 7 | 7 | 7 | 7 | 8 | 9
| Estimated Task Difficulty（0-10） |  | 4 | 4 | 3 | 5 | 5 | 4 | 4 | 6
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 8 | 9 | 8 | 10 | 9
27 | Test Cases and Requirements Test Coverage Report - Dashboard | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 9 | 8 | 10 | 7 | 9 | 5.875 | 2.875 | 2.375 | Mehul | Amrita | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 6 | 8 | 4 | 5 | 6 | 7 | 4 | 7
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 5 | 4 | 2 | 4 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 3 | 2 | 3 | 2 | 2 | 3 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 9 | 9 | 10 | 9 | 10 | 9
28 | Test Cases and Requirements Test Coverage Report - Personal Expenses | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 10 | 10 | 9 | 9 | 6.625 | 1.75 | 2.375 | Amrita | Anusha | Through Discussion | Yes | 2 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 8 | 6 | 7 | 8 | 7 | 6 | 5 | 6
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
29 | Test Cases and Requirements Test Coverage Report - Shared Expenses | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 10 | 9 | 10 | 10 | 9 | 6.625 | 1.75 | 2 | Anusha | Mehul | Through Discussion | Yes | 1 | Happy | 9.625
| Estimated Task Priority（0-10） |  | 8 | 7 | 7 | 8 | 7 | 6 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 9 | 10 | 10 | 8 | 10
30 | Test Cases and Requirements Test Coverage Report - My Friends | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 6.625 | 1.75 | 2.125 | Anusha | Amrita | Through Discussion | Yes | 1 | Happy | 9.75
| Estimated Task Priority（0-10） |  | 8 | 7 | 7 | 8 | 7 | 6 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 1 | 1 | 2 | 3 | 2 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
31 | Test Cases and Requirements Test Coverage Report - My Groups | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 10 | 6.5 | 1.875 | 2.25 | Anusha | Mehul | Through Discussion | Yes | 2 | Happy | 9.75
| Estimated Task Priority（0-10） |  | 6 | 7 | 7 | 7 | 8 | 6 | 6 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 3 | 2 | 2 | 1 | 3 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 1 | 2 | 2 | 3 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 10 | 10 | 8 | 10 | 10 | 10
32 | Test Cases and Requirements Test Coverage Report - Chat | Task Quality Evaluation (After Task Completed) | 9 | 10 | 9 | 10 | 10 | 10 | 10 | 9 | 6.625 | 1.75 | 2 | Nicklaus | Elliot | Through Discussion | Yes | 2 | Happy | 9.625
| Estimated Task Priority（0-10） |  | 8 | 7 | 7 | 8 | 7 | 6 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 8 | 10 | 10 | 10 | 9
33 | Test Cases and Requirements Test Coverage Report - Personal Account | Task Quality Evaluation (After Task Completed) | 9 | 10 | 8 | 10 | 8 | 10 | 9 | 9 | 6.75 | 2.25 | 2.5 | Daniel | Alex | Through Discussion | Yes | 1 | Happy | 9.125
| Estimated Task Priority（0-10） |  | 8 | 7 | 6 | 8 | 7 | 8 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 1 | 2 | 3 | 2 | 2 | 3 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
34 | Test Cases and Requirements Test Coverage Report - Notifications | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 6.625 | 1.75 | 2 | Alex | Kalki | Through Discussion | Yes | 1 | Happy | 9.75
| Estimated Task Priority（0-10） |  | 8 | 7 | 7 | 8 | 7 | 6 | 5 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 2 | 1 | 2 | 1 | 3 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
35 | Test Cases and Requirements Test Coverage Report - Informational Sections | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5.375 | 1.625 | 1 | Alex | Kalki | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 5 | 3 | 5 | 6 | 8 | 6 | 4 | 6
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 2
Estimated Time Required for the Task（1-14 Days） | bar: 1 to 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 9 | 10 | 10 | 9 | 10 | 10 | 9
36 | Presentation Slides - Product Introduction | Task Quality Evaluation (After Task Completed) | 10 | 10 | 9 | 9 | 10 | 9 | 7 | 9 | 5.125 | 2.625 | 1.75 | Nicklaus | Amrita | Through Discussion | Yes | 2 | Happy | 9.125
| Estimated Task Priority（0-10） |  | 5 | 6 | 4 | 5 | 6 | 7 | 3 | 5
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 4 | 4 | 2 | 3 | 2 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 2 | 2 | 1 | 2 | 3 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 9 | 10 | 10
37 | Presentation Slides - Design for Maintainability | Task Quality Evaluation (After Task Completed) | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 6 | 4 | 2 | Nicklaus | Daniel | Through Discussion | Yes | 2 | Happy | 9.75
| Estimated Task Priority（0-10） |  | 7 | 5 | 6 | 6 | 7 | 5 | 5 | 7
| Estimated Task Difficulty（0-10） |  | 5 | 4 | 3 | 4 | 4 | 4 | 3 | 5
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 3 | 2 | 2 | 2 | 1 | 2 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 9 | 9 | 9 | 10 | 9 | 8
38 | Presentation Slides - Software Quality Assurance | Task Quality Evaluation (After Task Completed) | 10 | 9 | 10 | 10 | 10 | 9 | 8 | 10 | 4.375 | 3.375 | 1.5 | Daniel | Nicklaus | Through Discussion | Yes | 2 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 5 | 4 | 3 | 5 | 6 | 4 | 3 | 5
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 3 | 3 | 5 | 4 | 4 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 8 | 10 | 9 | 8 | 10 | 10 | 9
39 | Presentation Slides - Project Management | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 9 | 8 | 9 | 9 | 10 | 9.25 | 3.25 | 1.5 | Daniel | Anusha | Through Discussion | Yes | 2 | Happy | 9.375
| Estimated Task Priority（0-10） |  | 9 | 10 | 10 | 9 | 9 | 8 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 3 | 3 | 3 | 5 | 3 | 4 | 3 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 10 | 9 | 10 | 9 | 10 | 9
40 | Presentation Slides - Risk Management | Task Quality Evaluation (After Task Completed) | 10 | 9 | 8 | 9 | 8 | 8 | 9 | 10 | 3.125 | 2.875 | 1.75 | Amrita | Anusha | Through Discussion | Yes | 2 | Happy | 8.875
| Estimated Task Priority（0-10） |  | 4 | 3 | 2 | 4 | 5 | 2 | 2 | 3
| Estimated Task Difficulty（0-10） |  | 3 | 4 | 2 | 3 | 2 | 3 | 4 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 9 | 10 | 9 | 9
41 | Presentation Slides - Architecture Overview | Task Quality Evaluation (After Task Completed) | 9 | 10 | 8 | 9 | 10 | 8 | 8 | 10 | 3.5 | 2.25 | 1.625 | Anusha | Amrita | Through Discussion | Yes | 2 | Happy | 9
| Estimated Task Priority（0-10） |  | 4 | 3 | 5 | 3 | 4 | 4 | 2 | 3
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 2 | 2 | 3 | 2 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 8 | 6 | 9 | 6 | 8 | 10